# Methodology Paper: Daily Action Plan & Checklist

## Target: Journal of Hazardous Materials Submission

## Start Date: February 25, 2026

## PHASE 1: GENERATE FIGURES, TABLES, AND MISSING DATA (Days 1-4)

## HOW TO RESUME

- Open a new conversation with Claude

- Share these project files: PROJECT_README.md, this session notes file, methodology_paper_outline.md, key_findings_for_paper.md, paper_daily_action_plan.md, chelator_project_roadmap.md

- Say: "I'm working on the methodology paper for my chelator ML project. Days 1-4 are complete (tables, figures, references). I'm ready to start Day 5 — writing Section 2.1 (PHREEQC Configuration and Parameter Design). See the session notes for where we left off."

- Claude will have full context to help write the Methods section

## KNOWN ISSUES / REMINDERS

- Kim et al. (2003) extraction percentages (50% and 90%) are estimates — verify against actual paper before submission

- Figure 7 (Streamlit screenshot) still needs to be created manually

- The label encoder stores no-chelator as "nan" (not "None") — relevant if app code is touched

- Figure 3 heatmap values differ from Day 1 summary table because heatmap filters to pH 7.0 only — this is correct

- Hasegawa citation: verify this is the correct paper for the soil extraction data points used in the benchmark

- AI disclosure statement needed in final paper acknowledgments

## PHASE 2: WRITE METHODS SECTION (Days 5-8)

Write Methods first — it's the easiest because you're describing what you did.

### Day 5 — Section 2.1: PHREEQC Configuration & Parameter Design

- Write 2.1.1: PHREEQC version, database choice, justification vs alternatives (~200 words)

- Write Table 1 caption and finalize the parameter space table

- Write the pH paragraph: why it's the master variable, protonation effects on chelators, hydroxide/carbonate speciation shifts (~200 words)

- Write the texture-DOC-Hfo coupling paragraph: why tied together, real-soil correlation, generalized two-layer model, specific values chosen (~200 words)

### Day 6 — Section 2.1 continued: Proxies and Simulation Execution

- Write the ionic strength paragraph: RI coastal rationale, three levels, counterintuitive chloride complexation finding (~200 words)

- Write the pe-moisture proxy paragraph: oxygen diffusion link, three conditions, acknowledge simplification (~150 words)

- Write the humic/fulvic modeling paragraph: what we did, why, limitations, NICA-Donnan as future improvement (~200 words)

- Write 2.1.3: Simulation execution — scenario count, batch pipeline, output parsing, target variable definition (~200 words)

### Day 7 — Sections 2.2 and 2.3: ML Pipeline & Validation

- Write 2.2.1: Feature engineering — 20 features, encoding, deliberate collinearity (~200 words)

- Write 2.2.2: Model selection — RF vs GB comparison, why GB won, hyperparameters, train/test split, cross-validation (~250 words)

- Write 2.2.3: Evaluation metrics — R², RMSE, CV R² (~100 words)

- Write 2.3.1: Tier 1 chemical logic — 8 rules, principle, tolerance thresholds (~250 words)

- Write 2.3.2: Tier 2 literature — methodology, measurement mismatch acknowledgment, mapping procedure, what we compared (~250 words)

### Day 8 — Section 2.4: Interface & Methods Review

- Write 2.4: Streamlit interface description — inputs, outputs, conversion logic (~200 words)

- Read through entire Methods section start to finish

- Check: does every parameter choice have a stated rationale?

- Check: are all numbers accurate (verify against actual data files)?

- Check: consistent units throughout (mg/L, mol/L, etc.)?

## PHASE 3: WRITE RESULTS AND DISCUSSION (Days 9-13)

### Day 9 — Section 3.1: PHREEQC Results Overview

- Write 3.1.1: Dataset overview with Table 3, variation in free metal (~300 words)

- Write 3.1.2: pH as dominant control, reference Figure 2, mechanistic explanation (~400 words)

### Day 10 — Sections 3.1.3-3.1.5: Chelator, Ionic, Texture Effects

- Write 3.1.3: Chelator effectiveness patterns by metal, dose-response, reference Figures 3 and 4 (~400 words)

- Write 3.1.4: Ionic strength effects — counterintuitive finding, RI implications, chloride complexation nuance (~300 words)

- Write 3.1.5: Texture and surface complexation, competing DOC effect (~200 words)

### Day 11 — Section 3.2: ML Performance

- Write 3.2: Model performance with Table 4, explain why R² so high, discuss Cu complexity (~300 words)

- Write 3.2.1: Feature importance analysis, reference Figure 5, connect to known geochemistry (~300 words)

### Day 12 — Section 3.3: Validation Results

- Write 3.3.1: Tier 1 results — 4 perfect passes, 4 edge-case "failures" with scientific explanations for each, reference Table and Figure 6 (~500 words)

- Write 3.3.2: Tier 2 results — what agreed (rankings, difficulty order, pH effects), what didn't (Zn magnitude), measurement domain mismatch discussion (~400 words)

### Day 13 — Sections 3.4-3.5: Interface & Limitations

- Write 3.4: Interface walkthrough with example RI case, reference Figure 7 screenshot (~300 words)

- Write 3.5: Limitations — equilibrium assumption, simplified OM, closed system, parameter range constraints, bench validation needed (~500 words) Frame each limitation with "what we plan to do about it"

## PHASE 4: WRITE INTRO, ABSTRACT, CONCLUSIONS (Days 14-16)

Write these last — easier once you know exactly what's in the paper.

### Day 14 — Introduction

- Write 1.1: Problem scope — contamination globally, in US, in RI specifically (~300 words)

- Write 1.2: Chelation chemistry fundamentals, current practice limitations (~400 words)

- Write 1.2 continued: Existing modeling and ML approaches, cite prior work (~300 words)

- Write 1.3: The gap, our novel approach, objectives statement (~300 words)

### Day 15 — Abstract & Conclusions

- Write Conclusions: 3 paragraphs summarizing accomplishment, key findings, significance and future work (~400 words)

- Write Abstract: 3 paragraphs — problem, what we did, key findings (~250 words)

- Write Highlights: 5 bullet points, each under 85 characters

- Draft Graphical Abstract concept (sketch or describe for later design)

### Day 16 — Supplementary Materials

- Prepare S1: Example PHREEQC input file with line-by-line annotations

- Prepare S2: Complete parameter value table with all unit conversions

- Prepare S3: Full Tier 1 validation details (all 8 rules, all violations)

- Prepare S4: Full Tier 2 literature comparison table

- Prepare S5: GitHub repository (or plan for it) — training data, model code, app code

## PHASE 5: POLISH AND SUBMIT (Days 17-21)

### Day 17 — Full Read-Through & Internal Review

- Print or export the full manuscript and read it straight through

- Mark any sections that feel weak, unclear, or repetitive

- Check all figure/table references in text match actual figure/table numbers

- Verify all numbers in text match the actual data

### Day 18 — Revisions

- Address all issues marked during read-through

- Ensure consistent terminology throughout (% free metal, not switching terms)

- Check that every figure and table is referenced in the text

- Verify reference list is complete — every in-text citation has a full reference

### Day 19 — Final Figures & Formatting

- Finalize all figures at publication resolution (300+ DPI, PDF or TIFF)

- Create the Graphical Abstract (required by J Hazard Mater)

- Format manuscript per J Hazard Mater author guidelines (check their Guide for Authors for specific requirements: font, spacing, heading style)

- Add AI disclosure statement to Acknowledgments

- Add Data Availability statement (link to GitHub repo or "available on request")

### Day 20 — Cover Letter & Final Check

- Write cover letter to editor (~300 words): - Why this paper fits J Hazard Mater - The 3 novel contributions - Statement that it's not under review elsewhere

- Final proofread of entire manuscript

- Check all author information, affiliations, contact details

- Confirm supplementary files are formatted correctly

### Day 21 — Submit

- Create account on Elsevier Editorial Manager (if not already)

- Upload manuscript, figures, supplementary materials, cover letter

- Select article type, keywords, suggest reviewers (optional but helpful)

- Submit and celebrate

## WHAT TO BRING TO EACH CLAUDE SESSION

When you sit down to work on a section, share:

- This checklist (so I know where you are)

- The methodology_paper_outline.md (in project files, I already have it)

- What you want to work on today: "I'm on Day 6, writing the ionic strength paragraph"

- Any draft text you've written that you want me to help refine

I can help you:

- Draft paragraphs based on your data and the outline

- Generate figures and tables from your training data

- Find and format specific references

- Review and tighten your writing

- Check scientific accuracy of claims

## QUICK REFERENCE: WORD COUNT TARGETS

| Section | Target Words |
| --- | --- |
| Abstract | 250 |
| Introduction | 1,200 |
| Methods | 2,500 |
| Results & Discussion | 3,000 |
| Conclusions | 400 |
| Total main text | ~7,350 |
| Figure captions | ~500 |
| Table captions | ~300 |
| Grand total | ~8,000 |

This is well within J Hazard Mater's guidelines.

## MOTIVATION TRACKER

| Phase | Days | Status |
| --- | --- | --- |
| Phase 1: Figures & Tables | 1-4 | [ ] |
| Phase 2: Methods | 5-8 | [ ] |
| Phase 3: Results & Discussion | 9-13 | [ ] |
| Phase 4: Intro, Abstract, Conclusions | 14-16 | [ ] |
| Phase 5: Polish & Submit | 17-21 | [ ] |